## Sheet1
ID | Date Raised | Risk Description | Likelihood | Impact | Severity | Owner | Mitigating Action | Contingent Action | Progress on actions | Status
1 | 01/29/2021 | Lack of previous experience will negatively impact the estimation and scheduling of the project | High | Medium | High | Tyler Znoj | Accept | N./A. | N./A. | Open
2 | 01/29/2021 | Some issues will be raised at the last minute which will disrupt a sprint's planning and scheduling | Low | High | Medium | Killian Kelly | Mitigate | Accept | N./A. | Open
3 | 01/29/2021 | The requirements may be imprecise which will cause confusion among the team | Medium | High | High | Abdul Sirawan | Mitigate | Accept | N./A. | Open
4 | 01/29/2021 | Unnecessary features will potentially be developed increasing the project length | Medium | Low | Low | Adrien Kamran | Avoid | Mitigate | N./A. | Open
5 | 01/29/2021 | If incorrectly designed, the information on the database may be lost when it crashes | Low | High | Medium | Qandeel Arshad | Avoid | N./A. | The database was implemented and tested | Closed
6 | 01/29/2021 | If the database isn't connected, sales data and manufacturing data will be lost | Low | High | Medium | Cedrik Dubois | Avoid | N./A. | The database was implemented and tested | Closed
7 | 01/29/2021 | If the system is not properly set up, changes in inventory may not be recorded | Low | High | Medium | Anthony Chraim | Avoid | N./A. | The system has yet to be fully integrated | Open
8 | 01/29/2021 | Items being potentially flagged as defective that aren't defective | Medium | Medium | Medium | Matthew Giancola | Avoid | Mitigate | The automatic defective detection system has not been implemented | Open
9 | 01/29/2021 | The UI may be misleading if designed improperly | Medium | Low | Low | Tyler Znoj | Mitigate | N./A. | The UI is constantly being refined | Open
10 | 01/29/2021 | User may not be logged out when inactive | Low | Low | Low | Killian Kelly | Avoid | N./A. | The automatic logout system functions as intended | Closed
11 | 02/19/2021 | Inadequate testing of features | Low | High | High | Abdul Sirawan | Mitigate | Accept | The new implemented features are constantly tested | Open
12 | 02/20/2021 | Inadequate comments and code clarity | Low | Low | Low | Tyler Znoj | Mitigate | N./A. | Refactoring sessions every sprint | Open
13 | 02/22/2021 | Part of the inventory not being properly displayed | Low | High | Medium | Adrien Kamran | Avoid | N./A. | The issue did not occur | Closed
14 | 02/23/2021 | Miscommunication amongst sub-teams | Low | High | Medium | Qandeel Arshad | Avoid | N./A. | This issue has not occurred | Open
15 | 02/23/2021 | Inventory does not update | Low | High | Medium | Cedrik Dubois | Avoid | N./A. | This issue has not occurred | Open
16 | 02/24/2021 | System events do not trigger upon user actions (workflow, emails, etc.) | Low | Medium | Low | Adrien Kamran | Avoid | N./A. | This issue has not occurred | Open
17 | 02/24/2021 | System does not generate documents, or generates docs with incorrect data | Low | High | Medium | Tyler Znoj | Avoid | N./A. | This issue cannot occur (as of Sprint 2) | Open
18 | 02/24/2021 | User cannot login with an existing account, or register a new one | Low | High | Medium | Abdul Sirawan | Avoid | N./A. | This issue has not occurred | Open
19 | 02/24/2021 | User gains accessed to unauthorized data | Low | High | Medium | Matthew Giancola | Avoid | N./A. | This issue has not occurred | Open
20 | 2021-04-03 | The system associates the wrong customer with a sale | Low | High | Medium | Killian Kelly | Avoid | N./A. | This issue has not occurred | Open
21 | 2021-07-03 | Users are able to use defective parts to manufacture products and other parts | Medium | Medium | Medium | Cedrik Dubois | Avoid | Mitigate | This issue has not occurred | Open
22 | 2021-08-03 | Edits to material lists won't be saved | Low | High | Medium | Tyler Znoj | Avoid | N./A. | This issue has not occurred | Open
23 | 2021-10-03 | Sale's shipping information won't update | Low | Low | Low | Tyler Znoj | Avoid | Accept | This issue has not occurred | Open
24 | 03/14/2021 | Sale's shipping information won't be generated | Low | High | Medium | Qandeel Arshad | Avoid | N./A. | This issue has not occurred | Open
25 | 03/16/2021 | Costs not being logged properly | Medium | High | High | Anthony Chraim | Avoid | N./A. | This issue has not occurred | Open
26 | 03/16/2021 | Material lists are not being displayed properly | Low | Medium | Low | Matthew Giancola | Avoid | Mitigate | This issue has not occurred | Open
27 | 03/17/2021 | User cannot access tabs authorized to them | Medium | High | High | Tyler Znoj | Avoid | Accept | In progress | Open